## Slide 1: OMA-COM-2011-0005-INP_SpamRep_Report_Honolulu Technical Plenary Presentation SpamRep Honolulu, USA
Submitted To: OMA COM
Date: 11 Feb 2011
Availability: Public OMA Confidential
Contact: David K. Smith, david.k.smith@att.com
Source: SpamRep Chair (SpamRep)
X
USE OF THIS DOCUMENT BY NON-OMA MEMBERS IS SUBJECT TO ALL OF THE TERMS AND CONDITIONS OF THE USE AGREEMENT (located at http://www.openmobilealliance.org/UseAgreement.html) AND IF YOU HAVE NOT AGREED TO THE TERMS OF THE USE AGREEMENT, YOU DO NOT HAVE THE RIGHT TO USE, COPY OR DISTRIBUTE THIS DOCUMENT.
THIS DOCUMENT IS PROVIDED ON AN "AS IS" "AS AVAILABLE" AND "WITH ALL FAULTS" BASIS.
Intellectual Property Rights
Members and their Affiliates (collectively, "Members") agree to use their reasonable endeavours to inform timely the Open Mobile Alliance of Essential IPR as they become aware that the Essential IPR is related to the prepared or published Specification. This obligation does not imply an obligation on Members to conduct IPR searches. This duty is contained in the Open Mobile Alliance application form to which each Member's attention is drawn. Members shall submit to the General Manager of Operations of OMA the IPR Statement and the IPR Licensing Declaration. These forms are available from OMA or online at the OMA website at www.openmobilealliance.org.

## Slide 2: WI/Release update: SpamRep 1.0 i/iii
Overall progress since last report
  TP ratified approval of the SpamRep V1.0 enabler as Candidate on 13 December 2010
►
▲
▼
▲

## Slide 3: WI/Release update: SpamRep 1.0 ii/iii
Plan for the next 3 months
  Work with IOP to progress the ETS and IOP activities
  Maintenance of the RD, AD, TS and XSD
Potential issues which MAY affect schedule
  None identified
►
▲
▼

## Slide 4: WI/Release update: SpamRep 1.0 iii/iii
WISPR last updated: 2011/02/11
Chart: 
| Candidate | CONRR Start | AD Approved | TS Start | RD Approved | AD Start | RD Start
Current
Previous
Original | 40299 | 40238 | 40148 | 39965 | 40026 | 39873 | 39815
Achieved | 40505 | 40369 | 40288 | 40065 | 40036 | 39889 | 39799
2011-02-11 | 0 | 1
 | Candidate | AD Approved | TS Start | RD Approved | AD Start | RD Start | CR Start
Original | 2010-05-01 | 2009-12-01 | 2009-06-01 | 2009-08-01 | 2009-03-01 | 2009-01-02 | 2010-03-01
Previous | 2010-09-01 | 2009-12-01 | 2009-06-01 | 2009-08-01 | 2009-03-01 |  | 2010-05-01
Current | 2010-11-05 | 2010-03-15 | 2009-09-09 | 2009-08-20 | 2009-05-04 |  | 2010-07-07
Achieved | 2010-11-23 | 2010-04-20 | 2009-09-09 | 2009-08-11 | 2009-03-17 | 2008-12-17 | 2010-07-10

## Slide 5: Documents nearing TP approval
None

## Slide 6: WG-level issues brought to TP’s attention
WG level issues
  None
Other items
  None

## Slide 7: Schedule of upcoming meetings
Conference Calls
  None planned. Will schedule on an ad-hoc basis as/if necessary
Interim Meeting
  None
Next F2F Meeting (Sorrento, Italy)
  None
Requested/Planned Joint Meeting(s)
  None