## Slide 1: OMA-TP-2011-0xyz-INP_SACMO_1.0_Slip_Request SACMO 1.0 Slip Request
Submitted To: TP
Date: 17 January 2011
Availability: Public OMA Confidential
Contact: Liny Tian, tianlinyi@huawei.com
David K. Smith, david.k.smith@att.com
Source: DM
X
USE OF THIS DOCUMENT BY NON-OMA MEMBERS IS SUBJECT TO ALL OF THE TERMS AND CONDITIONS OF THE USE AGREEMENT (located at http://www.openmobilealliance.org/UseAgreement.html) AND IF YOU HAVE NOT AGREED TO THE TERMS OF THE USE AGREEMENT, YOU DO NOT HAVE THE RIGHT TO USE, COPY OR DISTRIBUTE THIS DOCUMENT.
THIS DOCUMENT IS PROVIDED ON AN "AS IS" "AS AVAILABLE" AND "WITH ALL FAULTS" BASIS.
Intellectual Property Rights
Members and their Affiliates (collectively, "Members") agree to use their reasonable endeavours to inform timely the Open Mobile Alliance of Essential IPR as they become aware that the Essential IPR is related to the prepared or published Specification. This obligation does not imply an obligation on Members to conduct IPR searches. This duty is contained in the Open Mobile Alliance application form to which each Member's attention is drawn. Members shall submit to the General Manager of Operations of OMA the IPR Statement and the IPR Licensing Declaration. These forms are available from OMA or online at the OMA website at www.openmobilealliance.org.

## Slide 2: SACMO v1.0 Slip Request
New CONR start and Candidate/Approval Dates Request for W0193 – Software and Application Control Management Object (SACMO v1.0)
Reason for Slip Request :
  Initial Closure Review held on Dec 9 revealed that 3 key areas of the TS needed further technical detail before the group felt we could proceed to Consistency Review
  Responsibility for completing the missing sections of the TS were assigned to individual delegates
  Proximity to the December/January holiday period necessitates a 2 month slip
Revised Time Plan for the Slip Request
  CONR start: 2010-12-01  2011-02-01
  Release Approved as Candidate : 2011-03-15  2011-05-15

## Slide 3: SACMO v1.0 Approval Report
 | Candidate | AD Approved | TS Start | RD Approved | AD Start | RD Start | CR Start
Original | 2010-10-15 | 2010-08-01 | 2009-12-01 | 2010-02-01 | 2009-11-15 | 2009-11-15 | 
Previous | 2010-12-15 | 2010-08-01 | 2009-12-01 | 2010-02-01 |  |  | 
Current | 2011-03-15 | 2010-10-01 | 2010-03-01 | 2010-06-01 |  |  | 
Achieved |  | 2010-10-05 | 2010-04-26 | 2010-07-27 | 2009-11-15 | 2009-11-15 | 

## Slide 4
Recommendation
TP is recommended to agree on the new WISPR dates requested for SACMO1.0.