## Sheet1
List of DM WG Discussions and Decisions to handle for freezing LWM2M TS 1.0
GitHub issues used as guideline
last update : Thierry GARNIER / Gemalto 29/08/2016
| Issue # | Cat | Title | Status | Status
55 | #1 | P9 | Firmware update | CR | on-going CR
| #2 | P3 | Same or Separate DTLS Sessions for Register & Object Access ? | D&D | Discussion &Decision. Proposal :
| #6 | P7 | Cipher Suite | D&D | on-going discussion & CR
| #7 | P6 | Registration Flow | D&D | Discussion &Decision :.Proposal :
| #15 | P3 | Adding Server Instance can only be done by Boostrap Server | D&D | Discussion &Decision
| #21 |  | Single Instance Object | Req Answ | Look to Test Case 6.2.2 to the light of CR 104 and answer accordindly
| #24 | P4 | Specific Code for Manufacturer | D&D | Discussion &Decision. Proposal :
| #26 | IETF | OMA Media Type & CoAP CT : IETF values | W | Waiting for IETF Value
| #28 | help wanted | Observe is mandatory | D&D | Proposal : current spec is OK
| #33 | P0 | Queue Mode | CR | on-going CR
| #39 | P6 | Bootstrap Server & account purge | D&D | Discussion & Decision
| #42 | P7 | Wrong Size Key | CR | CR 101
| #43 | Extra Object | Issue in Conn Mgt | REQ CR | Clarification needed
| #44 | Extra Object | Conn Mgt Bearer | REQ CR | Conn Mgt : bearer Selection (à voir ID:0)
| #48 | P8 | Ellyptic Curve | CR | CR 101 (#42)
| #49 | P1 | Alternate Path & Bootstrap | Req CR | DM WG Discussion & Decision : 3 CRS 39 / 82 /83
| #60 | P8 | End-to-end Security | D&D | DM WG Discussion & Decision : LWM2M 1.1
| #62 | P6 | Bootstrap Msg Flow | D&D | DM WG Discussion & Decision : Proposal is linked to issue #91
| #67 | P1 | Discover & Read all Objects | D&D | DM WG Discussion & Decision : linked to discussion on issue#105, #76 but also #49
| #69 | P0 | Queue Mode | CR | on-going CR
| #71 | P3 | Observation Lifetime & registration | Req CR | Associated Observations MUST be released after De-Registration and certainly after Update Registration when IP Address (and/or Port) changed . Specify clearly that points in TS (which sections / which wording ..)
| #76 | P3 | linked to 105 / Observe Object | D&D | DM WG Discussion & Decision : leave CoAP compliance see #105
| #77 | P4 | Server Public Key resource(4) of Security object (0) should not be mandatory | D&D | DM WG Discussion & Decision : The main subject is to define without ambiguity what is a Mandatory resource and what is an Optional one . Proposal (also linked to the same question issue# )
| #80 | P0 | Queue Mode | CR | on-going CR
| #81 | help wanted | Update Supported Objects feature | To be Closed | Answer provided
| #82 | P5 | Key for Lifetime | D&D | DM WG Discussion & Decision :
| #83 | P5 | PUT request clarification for Write Attribute vs payload | To be Closed | Answer provided
| #84 | P5 | 5.3.2 Update / Lifetime-1sec could be used | D&D | DM WG Discussion & Decision : Proposal on lifetime formula (cf #issue 84)
| #86 | P3 | TLV content for multiple-instance objects with one instance | CR | CR 104
| #87 | P4 | Some Resources Of Device Object (ID:3) should be made mandatory | D&D | DM WG Discussion & Decision : Proposal : no change !!
| #88 | P9 | Both Package & URI are mandatory | CR | Firmware Update
| #90 |  | Millisecond precision | To be closed | CR agreed On OMA JSON fix
| #91 | P3 | nterleaved Bootstrap and regular requests | REQ CR | DM WG Discussion & Decision. Proposal : during Bootstrap phase (Bootstrap Server) any request of regular Server are ignored up to the Bootstrap finish is not received
| #92 | help wanted | SMS Port Number | REQ CR | Answer to provide
| #95 | help wanted | Coap URI |  | Clarification requested
| #98 | P9 | Queue Mode | CR | on-going CR
| #99 | P2 | Bootstrap Finish Clarify | D&D | DM WG Discussion & Decision :
| #104 | P0 | Queue Mode | CR | CR-going
| #105 | P3 | Observe Object | D&D | DM WG Discussion & Decision : must CoAP Compliance be respected, while LWM2M could be more efficient in supporting a better garnularity in Observe functionality . Proposal :: Observe /Object_ID : notification should return to the Server the full Object Instance containing the resource which has changed (only 1 instance, that's why Object Instance TLV is mandatory : CR104)
| #110 | P2 | Discover : no textual description in the TS section 8.2.4 | REQ CR | p66-67
| #111 | P2 | Some examples to be fixed (p27 ..) | REQ CR | Fixing/revisiting the examples is needed : already solved by pieces
| #115 | P0 | Queue Mode | CR | CR-going
| #116 |  | IPSO Issue | D&D | DM WG Discussion & Decision : must be solved by IPSO : however, also raises the point that IPSO (and other organization) have still to release their specification without introducing confusion on OMA registration
| #119 | XML | Arguments in the XSD | REQ CR | Current XSD (20160812) must be enhanced (annex K) Argument : [ none ¦ ["0"-"9"]{=String} {,["0"-"9"]{=String}}* ]
| #120 | P3 | Registration format | Answer + D&D | DM WG Discussion & Decision : Answer : text is correct ct=JSON and during registration has not to be specified Object per Object
| #122 | P4 | Connectivity Statistics (Object ID:7) issue | D&D | DM WG Discussion & Decision : Collection Duration should be removed (CR5) CR114
| #123 | P9 | Reboot & firmware update | CR & D&D | D&D : Firmware Update : reboot is a sanity rule for firmware update (opposite to software update)
| #124 | P9 | Deletion of Obj Instances after firmware Update | CR & D&D | Firmware Update : sanity rules (cleanup)
| #125 | P3 | Msg payload / Content Type | CR | CR 104 on going
| #126 | P7 | Update Registration & Sec Credentials Changes | REQ CR | DM WG Discussion & Decision : proposal in the issue
| #127 |  | Can OMA use Github for storing the XML of the Objects | Decision | DM WG Discussion & Decision : reply to do
| #128 | P2 | Errata SCR B.2.2 | REQ CR | CR114
| #129 |  | Errata | To be Closed | Duplicate #122
| #130 | P2 | Typos 6.2.3 | REQ CR | CR114
| #132 | P3 | Object Versioning & Bootstrap | CR | CR 113 on-going
| #133 | P2 | 6.2.3 & Registration Update | Answered