## Sheet1
List of DM WG Discussions and Decisions to handle for freezing LWM2M TS 1.0
GitHub issues used as guideline
last update : Thierry GARNIER / Gemalto 25/10/2016
| Issue # | Cat | Title | Status | Status (History) | Comments for Github | Who | Actions
55 | #1 | P9 | Firmware update |  | on-going CR TS |  |  | To Be Closed
| #2 | P3 | Same or Separate DTLS Sessions for Register & Object Access ? | D&D | Discussion &Decision. Proposal :
| #6 | P7 | Cipher Suite | CR | on-going discussion | CBC with RFC 7366 (conditional mandatory) , CCM8 mandatory. Note : 1.1 would be deprecate CBC CR102 | Hannes | To Be Closed
| #7 | P6 | Registration Flow | D&D | Discussion &Decision :.Proposal :
| #15 | P3 | Adding Server Instance can only be done by Boostrap Server | Answ | Discussion &Decision Decision : Answer is on the portal, | Have to go through bootstrap server in 1.0 and 1.1 we can revisit the problem. Kindly explain the needed use cases. | Thierry | To Be Closed
| #21 |  | Single Instance Object | Answ | Look to Test Case 6.2.2 to the light of CR 104 and answer accordindly Decision : Answer is on the portal | To have same request on mulitple instance and single instance object. Write or Read, single instance object send explicitly instance 0. | Thierry | To Be Closed
| #24 | P4 | Specific Code for Manufacturer | D | Discussion &Decision Decision | In object 3, resource 11, error code, (9-199, reserved) and (200-255) private codes to be freely used. |  | CR to Do
| #26 | IETF | OMA Media Type & CoAP CT : IETF values | W | Waiting for IETF Value
| #28 | help wanted | Observe is mandatory | Answ | Proposal : current spec is OK Decision | LWM2M observe is mandatory for server and client, it is not to be considered one to one with CoAP spec | Thierry | To Be Closed
| #33 | P0 | Queue Mode | CR | CR117 |  |  | To Be Closed
| #39 | P6 | Bootstrap Server & account purge | D&D | Discussion & Decision : at least to review definitions (persistent keys ) | Persistent Key could be changed to Long Term key, non persistent key could be changed to temporary key, check with Friedhelm and Richard | Hannes
| #42 | P7 | Wrong Size Key | CR | CR 101 |  | Hannes | To be Closed
| #43 | Extra Object | Issue in Conn Mgt | REQ CR | Clarification needed
| #44 | Extra Object | Conn Mgt Bearer | REQ CR | Conn Mgt : bearer Selection (à voir ID:0)
| #48 | P8 | Ellyptic Curve | CR | CR 101 (#42) |  | Hannes | To be Closed
| #49 | P1 | Alternate Path & Bootstrap | CR | DM WG Discussion & Decision : 3 CRS 39 / 82 /83 CR 123
| #60 | New Req | End-to-end Security | Answ | DM WG Discussion & Decision : LWM2M 1.1 New Req LWM2M 1.1 | To be closed for 1.0, DM WG would take this as part of LWM2M v1.1, do provide the use case for e2e security. | DM WG/ Hannes | to create e2e security paragraph in v1.1 , RD for capturing the use cases.. GitHub need to close the issue with 1.1 would address this issue
| #62 | P6 | Bootstrap Msg Flow | D&D | DM WG Discussion & Decision : Proposal is linked to issue #91
| #67 | P1 | Discover & Read all Objects | D | DM WG Discussion & Decision : linked to discussion on issue#105, #76 but also #49 |  | Thierry | CR to do
| #69 | P0 | Queue Mode | CR | on-going CR CR 117 |  |  | To Be Closed
| #71 | P3 | Observation Lifetime & registration | Answ | Associated Observations MUST be released after De-Registration and certainly after Update Registration when IP Address (and/or Port) changed . Specify clearly that points in TS (which sections / which wording ..) | issue 1) De-register is clearly defined in the TS, cancel all associated observations issue 2) Update registration does not impact on the still existing object/object instance/reources | Thierry
| #76 | P3 | linked to 105 / Observe Object | D | DM WG Discussion & Decision : leave CoAP compliance see #105
| #77 | P4 | Server Public Key resource(4) of Security object (0) should not be mandatory | D&D | DM WG Discussion & Decision : The main subject is to define without ambiguity what is a Mandatory resource and what is an Optional one . Proposal (also linked to the same question issue# 43 ) |  | Nicolas | Persistent Key could be changed to Long Term key, non persistent key could be changed to temporary key, check with Friedhelm and Richard
| #80 | P0 | Queue Mode | CR | CR 117 |  |  | To Be Closed
| #81 | help wanted | Update Supported Objects feature | Answ | Answer provided |  |  | To Be Closed
| #82 | P5 | Key for Lifetime | D&D | DM WG Discussion & Decision : toi be revisited to the light of long term / short time definition
| #83 | P5 | PUT request clarification for Write Attribute vs payload | Answ | Answer provided |  |  | To Be Closed
| #84 | P5 | 5.3.2 Update / Lifetime-1sec could be used | D&D | DM WG Discussion & Decision : Proposal on lifetime formula (cf #issue 84) |  | Nicolas | Reference to section from CoAP RFC should be added to 5.3.1 & 5.3.2 and possible example from CoAP RFC formula to be added to LWM2M v1.0 TS. Note about not having too short a lifetime
| #86 | P3 | TLV content for multiple-instance objects with one instance | CR | CR 104 |  | Thierry | To Be Closed
| #87 | P4 | Some Resources Of Device Object (ID:3) should be made mandatory | Answ | DM WG Discussion & Decision : no change !! | Not possible to define these set of mandatory resources on which everyone has consensus. | Thierry | ToBe Closed
| #88 | P9 | Both Package & URI are mandatory | CR | Firmware Update |  | Thierry, Joaquin | Appendix D (also copied to Definitions) Mandatory: if this field is “Mandatory”, then the LWM2M MUST support this Object/resource. Optional: then the LWM2M SHOULD support this Object/resource. (for LWM2M v1.1) Conditional : then the LWM2M MUST support in certain conditions as explained in the TS for this object/resource
| #90 |  | Millisecond precision | To be closed | CR agreed On OMA JSON fix
| #91 | P3 | Interleaved Bootstrap and regular requests | CR | DM WG Discussion & Decision. Proposal : during Bootstrap phase (Bootstrap Server) any request of regular Server are ignored up to the Bootstrap finish is not received | During the subsequent bootstrap's of the device, the device would ignore and flush all the previous states in the device and starts fresh further to the bootstrap completion. (to be added in section 5.2) | Thierry CR126 | To be Closed
| #92 | help wanted | SMS Port Number | Answ | Answer to provide Answer Provided | Refer 3GPP TS 23.040, section 9.2.3.24 for details of the port. LWM2M TS is based on this addressing mode, which is described in section 7.2 | Thierry | To be Closed
| #95 | help wanted | Coap URI |  | Clarification requested | The example would be updated as it is not inline with other latest changes | David | To be Closed
| #98 | P9 | Queue Mode | CR | on-going CR ACK timeout now and Post /qm for v1.1 (CR117) |  | Hannes | To Be Closed
| #99 | P2 | Bootstrap Finish Clarify | Answ | DM WG Discussion & Decision : Decision | To get more clarity on the problem To be closed | Thierry David
| #104 | P0 | Queue Mode | CR | CR117 |  |  | To Be Closed
| #105 | P3 | Observe Object | D | DM WG Discussion & Decision : must CoAP Compliance be respected, while LWM2M could be more efficient in supporting a better garnularity in Observe functionality . Proposal :: Observe /Object_ID : notification should return to the Server the full Object Instance containing the resource which has changed (only 1 instance, that's why Object Instance TLV is mandatory : CR104) Decision | Based on CoAP 1.0, LWM2M v1.0 has covered observe. The new use cases would be addressed with LWM2M v1.1. The new use cases captured are - General observe on an object should send only changed resources/instances - Observe on multiple instances, same resource needs to be addressed | Thierry | Req Answ
| #110 | P2 | Discover : no textual description in the TS section 8.2.4 | CR | p66-67 CR127 |  | Thierry | To Be Closed
| #111 | P2 | Some examples to be fixed (p27 ..) | CR | Fixing/revisiting the examples is needed : already solved by pieces |  |  | To Be Closed
| #115 | P0 | Queue Mode | CR | CR117 |  |  | To Be Closed
| #116 |  | IPSO Issue | D&D | DM WG Discussion & Decision : must be solved by IPSO : however, also raises the point that IPSO (and other organization) have still to release their specification without introducing confusion on OMA registration |  | Joaquin | Tagged to be closed
| #119 | XML | Arguments in the XSD | REQ CR | Current XSD (20160812) must be enhanced (annex K) regarding arguments * |  | DM WG | To discuss further, need new set of requirements for the tool
| #120 | P3 | Registration format | Answer + D&D | DM WG Discussion & Decision : Answer : text is correct ct=JSON and during registration has not to be specified Object per Object |  | Julien | To clarify the GitHub issue
| #122 | P4 | Connectivity Statistics (Object ID:7) issue | D | DM WG Discussion & Decision : Collection Duration should be removed (CR5) CR114 | Sierra cleanup | Nicolas | To bring a CR to clean up
| #123 | P9 | Reboot & firmware update | CR | D&D : Firmware Update : reboot is a sanity rule for firmware update (opposite to software update) Decision CR118 |  | Hannes | To Be Closed
| #124 | P9 | Deletion of Obj Instances after firmware Update | D | Firmware Update : sanity rules (cleanup) Decision |  | Thierry | To Be Closed
| #125 | P3 | Msg payload / Content Type | CR | CR 104 |  | Thierry | To Be Closed
| #126 | P7 | Update Registration & Sec Credentials Changes | CR | DM WG Discussion & Decision Decision CR 120 | Server Policy dependent on the security changes | Hannes | To Be Closed
| #127 |  | Can OMA use Github for storing the XML of the Objects | Decision | DM WG Discussion & Decision : reply to do |  | Joaquin | At this time not to host XML in GitHub
| #128 | P2 | Errata SCR B.2.2 | TS | CR114 TS |  | Thierry | Closed
| #129 |  | Errata | Answ | Duplicate #122 |  | Thierry | To Be Closed
| #130 | P2 | Typos 6.2.3 | TS | CR114 TS |  | Thierry | To Be Closed
| #132 | P3 | Object Versioning & Bootstrap | TS | CR 113 on-going TS |  | Thierry | Closed
| #133 | P2 | 6.2.3 & Registration Update | Answ |  | Examples Required | Thierry
| #134 |  | Outdated IETF references | D&D | Problem of outdated refrences
| #135 |  | More Discover ambiguities | Answ | CR132 is inline with the Answer (one issue is Tab6 5.3.1) |  |  | To Be Closed
| #136 |  | Firmware update
| #137 |  | Observation lifetime, registration interface, and DTLS sessions | S | Influence of DTLS on upper layers
| #138 | New Req | LWM2M Security - X.509 DM Enrollment Using CSR | Answ | New requirement for LwM2M 1.1 |  |  | To Be Closed
| #139 |  | DTLS credentials for CoAP Firmware Download Server used for /5/0/1 | S | ??????????????????
| #140 |  | Resource lifecycle ambiguity | Answ | Too many issues in the same issue : many should be covered after Singapore (hope so)
| #141 | Test | LightweightM2M-1.0-int-105 test (Initial Registration to Bootstrap Server) confusion | Answ | Test is Invalid (105) |  |  | To Be Closed
| #142 |  | Bug in Observe with pmin example | CRreq | Bug 10 instead of 1 ( 8.2.4)
| #143 |  | DTLS SMS Reference Outdated | Answ | CR129 |  | Hannes | To Be Closed
| #144 |  | Terminology for Non-persistent Key vs. Persistent Key | S | Bootstrap
| #145 |  | 5.2.2.3 Client Initiated Bootstrap when "Register" failed | S | Client initiated bootstrap triggers condition
| #146 |  | Client Registration Interface and Bootstrap Interface with SMS Binding | S | What is the correct way to send Register messages when current Binding is set to "S", "SQ", "US" or "UQS"?
| #147 |  | Define relation of "Factory Reset" /3/0/5 (E.4) and "bootstrap" | S | Factory Reset issue : Purge Boostrap Account ??
| #148 |  | Exact meaning of "MSISDN | D&D | adding a normative reference for the "MSISDN" term and perhaps adding an example that would demonstrate its correct format.
| #149 |  | PSK identity for DTLS over SMS | D&D | there seem to be no resource to configure the identity |  | Thierry / Padu
| #150 |  | Exact semantics of Binding change | D&D
| #151 |  | E 1.1.1, relation of key size and cipher suite | CR |  | CR139 to be agreed | Hannes | To Be Closed
| #152 |  | Bootstrap Server Account cannot be properly handled during the bootstrap procedure | D&D | BS is not able to prevent collision allocation on Security Object Instance ID
| #153 |  | Reporting errors during bootstrap | Answ | Questions : BS stage : 1) WRITE Object instance, Object /Resource not supported by the Client ? 2) WRITE Object Instance with missing Mandatory Resources ? | CR 150 ; but improvment needed | David Thierry
| #154 |  | Access Control configuration during Bootstrap | Answ | waiting for comment onTS with CR150 |  | Thierry
#155
| #156 |  | Unit of SMNC (4/0/9) | REQ CR | Resource 9 of Connectivity Monitoring has no unit | Unit % must be removed
| #157 |  | BS deletes all instances scenario | Answ |  |  | Thierry | To Be Closed
| #158 |  | LightweightM2M-1.0-int-104 Test Case: Receiving SMS capability |  | Test Case 104