## Slide 1: OMA-CD-2011-0106-INP_TAS_WP_Update_Vancouver.pptx Work Program of TAS Vancouver
Submitted To: CD
Date: 1 Sep, 2011
Availability: Public OMA Confidential
Contact: Jin peng, peng.jin1@zte.com.cn
Source: TAS Champion
X
USE OF THIS DOCUMENT BY NON-OMA MEMBERS IS SUBJECT TO ALL OF THE TERMS AND CONDITIONS OF THE USE AGREEMENT (located at http://www.openmobilealliance.org/UseAgreement.html) AND IF YOU HAVE NOT AGREED TO THE TERMS OF THE USE AGREEMENT, YOU DO NOT HAVE THE RIGHT TO USE, COPY OR DISTRIBUTE THIS DOCUMENT.
THIS DOCUMENT IS PROVIDED ON AN "AS IS" "AS AVAILABLE" AND "WITH ALL FAULTS" BASIS.
Intellectual Property Rights
Members and their Affiliates (collectively, "Members") agree to use their reasonable endeavours to inform timely the Open Mobile Alliance of Essential IPR as they become aware that the Essential IPR is related to the prepared or published Specification. This obligation does not imply an obligation on Members to conduct IPR searches. This duty is contained in the Open Mobile Alliance application form to which each Member's attention is drawn. Members shall submit to the General Manager of Operations of OMA the IPR Statement and the IPR Licensing Declaration. These forms are available from OMA or online at the OMA website at www.openmobilealliance.org.

## Slide 2: WI/Release update: TAS1.0 i/ii
Overall progress since last report
  AD completed, but need enhancement
    IAP support agreed
    Identified the need for Interfaces by TAS Client
    More description of the functional components needed
  TS in progress
    Application state management in the Storefront agreed
    15 messages agreed
    Identified the need to investigate possible security mechanisms for TAS
Plan for the next 3 months
  Further improvement to the AD part: e.g. interfaces by TAS Client
  Make progress on the TS part: e.g. New sections for functionalitiess and procedures
Potential issues which MAY affect schedule
  TS start was delayed for 2 months and
  Much work to do to complete the TS
►
▲
▼
Will be slipped

## Slide 3: WI/Release update: TAS 1.0 ii/ii
WISPR last updated: 2011-09-01
 | Candidate | AD Approved | TS Start | RD Approved | AD Start | RD Start | CR Start
Original | 2012-02-01 | 2011-05-01 | 2011-05-01 | 2011-01-01 | 2010-11-01 | 2010-08-01 | 2011-11-01
Previous |  |  |  |  | 2010-11-01 |  | 
Current |  |  |  |  |  |  | 
Achieved |  |  | 2011-06-28 |  |  | 2010-08-19 |