- Work Item Status and Planning Report

| Title: | Report on WID 0094 SVG for the Mobile Domain | OMA Confidential |
| --- | --- | --- |
| WID Document: | OMA-WID_0094-SVG-for-the-Mobile-Domain-V1_0-20040428-S |  |
| Report Date: | 31st January 2004 |  |
| Reporting Group: | BAC-MAE |  |
| Contact Person: | Bennett Marks, Nokia, Bennett.marks@nokia.com |  |

- General Description

SVG for the Mobile Domain will investigate the requirements for supporting SVG on limited mobile devices. It is intended that the requirements be shared with W3C and that the endorsement of a profile of SVG be included in an upcoming Browsing Enabler Release

- Current Status

  - Status for Enabler Release  v1.0

- Work Progress on Key Stages

| Requirements | Status: Under review External Coordination: W3, ISO/IEC. |
| --- | --- |
| Architecture | Status: n/a Source Technologies: W3M SMIL, probably Tiny 1.2 profile but this is a TBD |
| Specification Creation | Status: not started, |
| Testing | Status: Not started Testing Considerations: tbd |

Table 1 - Work Progress for Enabler Release

- OMA dependencies on unapproved standards or specification:

| Organization | Area (WG) | Specification/Enabler | Expected Approval |
| --- | --- | --- | --- |

Table 2 – Dependencies on Unapproved Specifications

- Documents

  - Docs for Enabler Release 1.0

| Document Storage Location | BAC-MAE |
| --- | --- |
| Requirements Document | OMA-SvgMobileDomain-V1_0_2-20041202-D |
| Architecture Document | <AD name> |
| Specifications | To be determined based on a) the need, and b) the route to produce new specifications. |
| Support files (XML/DTD/etc) | TBD |
| ERELD | TBD |
| Test reports | <list of test reports> |
| Review Reports | OMA-RDRR-SVGMobileDomain-V1_0_2-20041202-D |

Table 3 – Information on Documents

- Schedule and Planning Information

| Milestone | Achieved Date | Current Plan | Previous Plan |
| --- | --- | --- | --- |
| WID |  |  |  |
| WID Approval | 22/03/2004 | 22/03/2004 | 22/03/2004 |
| WID Completion | (date) | (date) | (date) |
| Enabler Release <EnabRelName> in <FuncArea> Area (repeat this and following lines for each release) |  |  |  |
| Requirement Doc Work Started (w/Req WG) | 06/2004 | 6/2004 | 6/2004 |
| Requirement Doc Review Started | 11/2004 | 11/2004 | 11/2004 |
| Requirement Doc Review Completed | 12/2004 | 12/2004 | (date) |
| Requirement Doc Approved by TP | 01/2005 | 01/2005 | 12/2004 |
| Architecture Doc Work Started (w/Arch WG) | (date) | 12/2004 | 12/2004 |
| Architecture Doc Review Started | (date) | Tbd | Tbd |
| Architecture Doc Review Completed | (date) | Tbd | Tbd |
| Detailed Specification Development Started | (date) | 12/2004 | 12/2004 |
| Consistency Review Started | (date) | 2Q/2005 | 1Q/2005 |
| Consistency Review Completed | (date) | 2Q/2005 | 1Q/2005 |
| Enabler Package Approved as Candidate by TP | (date) | 3Q/2005 | 2Q/2005 |
| Test Planning Completed | (date) | (date) | (date) |
| Test Specifications Completed | (date) | (date) | (date) |
| Test Activities Completed | (date) | (date) | (date) |
| Enabler Package Approved by Technical Plenary | (date) | 1Q2006 | (date) |

Table 4 – Schedule Information

| First Rescheduled Milestone | Reason for Revised Planning | Corrective Actions |
| --- | --- | --- |
| Enabler Release <EnabRelName> in <FuncArea> Area (repeat this and following lines for each release) |  |  |

Table 5 – Detailed Information on Rescheduled Milestones