## Slide 1: OMA-DM-2013-0071-INP_GwMO_v1.1_Slippage_request GwMO v1.1 Slip Request
Submitted To: DM
Date: 24th July 2013
Availability: Public OMA Confidential
Contact: S. Ramanan, NEC S.Ramanan@emea.nec.com
Norio Uchida, NEC n-uchida@cq.jp.nec.com
Source: DM WG (WI Champion & TS Editor)
X
USE OF THIS DOCUMENT BY NON-OMA MEMBERS IS SUBJECT TO ALL OF THE TERMS AND CONDITIONS OF THE USE AGREEMENT (located at http://www.openmobilealliance.org/UseAgreement.html) AND IF YOU HAVE NOT AGREED TO THE TERMS OF THE USE AGREEMENT, YOU DO NOT HAVE THE RIGHT TO USE, COPY OR DISTRIBUTE THIS DOCUMENT.
THIS DOCUMENT IS PROVIDED ON AN "AS IS" "AS AVAILABLE" AND "WITH ALL FAULTS" BASIS.
Intellectual Property Rights
Members and their Affiliates (collectively, "Members") agree to use their reasonable endeavours to inform timely the Open Mobile Alliance of Essential IPR as they become aware that the Essential IPR is related to the prepared or published Specification. This obligation does not imply an obligation on Members to conduct IPR searches. This duty is contained in the Open Mobile Alliance application form to which each Member's attention is drawn. Members shall submit to the General Manager of Operations of OMA the IPR Statement and the IPR Licensing Declaration. These forms are available from OMA or online at the OMA website at www.openmobilealliance.org.

## Slide 2: WISPR date slips for approval
New WISPR date request for WID 0272 GwMO v1.1
Justification:
  Knock on effect from the delay in RD & AD completion (about two months).
  Delay in progressing the specification development (i.e., awaiting for response from BBF and ZigBee Alliance )
  Allow at least two face-to-face meetings (Bangkok, Las Vegas) for TS discussions.
    Note that taking into account the December holidays, consistency review start date is moved to January 2014.
Corrective action:
  Progress in parallel the specification development for DM Gateway adaptation for various non-OMA DM protocols
  Encourage offline discussions for review and build consensus on the proposals
“Hard” WISPR dates affected:
  Consistency/Closure Review Start : Existing Date: 2013-09-15  New Date: 2014-01-08
  Release Approved as Candidate: Existing Date: 2013-10-15  New Date: 2014-02-28

## Slide 3: Slip Report
Chart: 
| Release approved as candidate | Architecture - Approved as Candidate | RD Approved as Candidate | Knock on effect from the delay in RD & AD completion (about two months). Delay in progressing the specification development (i.e., awaiting for response from BBF and ZigBee Alliance) Allow at least two face-to-face meetings (Bangkok, Las Vegas) for TS
Proposed | 41698
Current | 41562 | 41425 | 41334
Original | 41562 | 41338 | 41274
2013-08-08 | 0 | 1
Milestone | Original Date | Current Target | Proposed Target | Slippage
RD as candidate | 2012-12-31 |  |  | 
AD as candidate | 2013-03-05 | 2013-05-31 |  | 
ERP/RRP as candidate | 2013-10-15 | 2013-10-15 | 2014-02-28 | 4 months
Reason for delayed milestones | Knock on effect from the delay in RD & AD completion (about two months). Delay in progressing the specification development (i.e., awaiting for response from BBF and ZigBee Alliance) Allow at least two face-to-face meetings (Bangkok, Las Vegas) for TS |  |  | 
Corrective action | Progress in parallel the specification development for DM Gateway adaptation for various non-OMA DM protocols Encourage offline discussions for review and build consensus on the proposals |  |  | 

## Slide 4: Recommendation
TP is kindly requested to agree on the new WISPR dates for the GwMO v1.1 work item.