| # OMA Work Item Status and Planning Report Procedure |  |  |  |
| --- | --- | --- | --- |
| Approved Version 1.2 – 23 Sep 2009 |  |  |  |
| Open Mobile Alliance |  |  |  |
| OMA-ORG-WISPR_Procedure-V1_2-20090923-A |  |  |  |

Use of this document is subject to all of the terms and conditions of the Use Agreement located at http://www.openmobilealliance.org/UseAgreement.html.

Unless this document is clearly designated as an approved specification, this document is a work in process, is not an approved Open Mobile Alliance™ specification, and is subject to revision or removal without notice.

You may use this document or any part of the document for internal or educational purposes only, provided you do not modify, edit or take out of context the information in this document in any manner.  Information contained in this document may be used, at your sole risk, for any purposes.  You may not use this document in any other manner without the prior written permission of the Open Mobile Alliance.  The Open Mobile Alliance authorizes you to copy this document, provided that you retain all copyright and other proprietary notices contained in the original materials on any copies of the materials and that you comply strictly with these terms.  This copyright permission does not constitute an endorsement of the products or services.  The Open Mobile Alliance assumes no responsibility for errors or omissions in this document.

Each Open Mobile Alliance member has agreed to use reasonable endeavors to inform the Open Mobile Alliance in a timely manner of Essential IPR as it becomes aware that the Essential IPR is related to the prepared or published specification.  However, the members do not have an obligation to conduct IPR searches.  The declared Essential IPR is publicly available to members and non-members of the Open Mobile Alliance and may be found on the “OMA IPR Declarations” list at http://www.openmobilealliance.org/ipr.html.  The Open Mobile Alliance has not conducted an independent IPR review of this document and the information contained herein, and makes no representations or warranties regarding third party IPR, including without limitation patents, copyrights or trade secret rights.  This document may contain inventions for which you must obtain licenses from third parties before making, using or selling the inventions.  Defined terms above are set forth in the schedule to the Open Mobile Alliance Application Form.

NO REPRESENTATIONS OR WARRANTIES (WHETHER EXPRESS OR IMPLIED) ARE MADE BY THE OPEN MOBILE ALLIANCE OR ANY OPEN MOBILE ALLIANCE MEMBER OR ITS AFFILIATES REGARDING ANY OF THE IPR’S REPRESENTED ON THE “OMA IPR DECLARATIONS” LIST, INCLUDING, BUT NOT LIMITED TO THE ACCURACY, COMPLETENESS, VALIDITY OR RELEVANCE OF THE INFORMATION OR WHETHER OR NOT SUCH RIGHTS ARE ESSENTIAL OR NON-ESSENTIAL.

THE OPEN MOBILE ALLIANCE IS NOT LIABLE FOR AND HEREBY DISCLAIMS ANY DIRECT, INDIRECT, PUNITIVE, SPECIAL, INCIDENTAL, CONSEQUENTIAL, OR EXEMPLARY DAMAGES ARISING OUT OF OR IN CONNECTION WITH THE USE OF DOCUMENTS AND THE INFORMATION CONTAINED IN THE DOCUMENTS.

© 2009 Open Mobile Alliance Ltd.  All Rights Reserved.
Used with the permission of the Open Mobile Alliance Ltd. under the terms set forth above.

Contents

1.	Scope	3

2.	References	3

2.1	Normative References	3

2.2	Informative References	3

3.	Terminology and Conventions	3

3.1	Conventions	3

3.2	Definitions	3

3.3	Abbreviations	3

4.	Introduction	3

4.1	Version 1.0	3

4.1.1	Version 1.1	3

4.2	Version 1.2	3

5.	Elements of the WISPR	3

5.1	WISPR Components	3

5.2	Responsibilities of the WI and IOP Champions	3

5.2.1	WI Champion	3

5.2.2	IOP Champion	3

5.3	Milestones in the WISPR	3

6.	WISPR Procedures	3

6.1	WISPR information following approval of new WIDs	3

6.2	Required Updates to the WISPR	3

6.2.1	Delegated Work for a Work Item	3

6.2.2	Changes to the WISPR Schedule	3

6.3	REL Analysis of the Work Program	3

6.4	Process steps and responsibilities for Work programme updates	3

Appendix A.	Change History (Informative)	3

A.1	Approved Version History	3

Tables

Table 1: Milestone Determination Events	3

Table 2: Process steps	3

# Scope

This document defines the OMA Work Item Status and Planning Report (WISPR) procedures.

# References

## Normative References

| [RFC2119] | “Key words for use in RFCs to Indicate Requirement Levels”, S. Bradner, March 1997, URL:http://www.ietf.org/rfc/rfc2119.txt |
| --- | --- |
| [OMAPROC] | “OMA Organization and Processes”. Open Mobile Alliance. OMA-Process-V1_6 or later. URL:http//www.openmobilealliance.org/ |

## Informative References

| None. |  |
| --- | --- |

# Terminology and Conventions

## Conventions

The key words “MUST”, “MUST NOT”, “REQUIRED”, “SHALL”, “SHALL NOT”, “SHOULD”, “SHOULD NOT”, “RECOMMENDED”, “MAY”, and “OPTIONAL” in this document are to be interpreted as described in [RFC2119].

All sections and appendixes, except “Scope” and “Introduction”, are normative, unless they are explicitly indicated to be informative.

## Definitions

| Approved | The capitalized word “Approved” refers to a Specification, an Enabler Release or a Reference Release that has reached Approved status as defined in [OMAPROC]. When the word appears as lower case “approved”, normal English meaning is applied. |
| --- | --- |
| Candidate | The capitalized word “Candidate” refers to a Specification, an Enabler Release or Reference Release that has reached Candidate status as defined in [OMAPROC]. |
| Enabler Release | A set of technical specifications and white papers which form a formal deliverable of OMA that can be implemented in products and solutions and which can also be tested for interoperability |
| External Dependencies | The list of unpublished external deliverables normatively referenced by this Release |
| Group | The Technical Plenary, Working Group, Sub-Working Group, or Committee. |
| Internal Dependencies | The list of OMA Releases on which this Release depends |
| Reference Release | A set of specifications and/or white papers which form a formal deliverable of OMA. The release can be referenced or otherwise used to support implementable enabler releases, but it cannot by itself be implemented in products. |
| Release | The capitalized word Release refers to a Reference Release or an Enabler Release. When the word appears as lower case “release”, the normal English meaning is applied. |
| Sub Working Group | A group chartered by a Working Group to perform specific technical work within the domain of the parent Working Group. |
| WI Champion | The person who will be the main contact for the Work Programme Secretary and REL in relation to the WI and WISPR information |
| Work Programme Secretary | The Document Support Officer (DSO) who is in charge of handling the Work Programme report. |
| Working Group | A group chartered by the Technical Plenary to perform specific technical work |

## Abbreviations

| AD | Architecture Document |
| --- | --- |
| CONR | Consistency Review |
| DSO | Document Support Office or Document Support Officer |
| ERP | Enabler Release Package |
| ETRRR | Enabler Test Requirements Review Report |
| EVP | Enabler Evaluation Plan |
| IOP | Interoperability Working Group |
| OMA | Open Mobile Alliance |
| RD | Requirements document |
| REL | Release Planning and Management Committee |
| RRP | Reference Release Package |
| SUP | Support file |
| TP | Technical Plenary |
| TS | Technical Specification |
| WG | Working Group |
| WI | Work Item |
| WID | Work Item Document |
| WISPR | Work Item Status and Planning Report |
| WP | White Paper |
| WPS | Work Programme Secretary |

# Introduction

The WISPR procedures are applicable for Releases until they reach final approval. The data is used to produce reports and presentations.

## Version 1.0

The Work Programme (WP) tool supports web based entry. By making use of information already available on the portal, the tool significantly reduces the amount of information entered by Work Item Champions. It adds a set of validation rules to improve the quality of the data. Periodically, all Working Groups are requested to update the data (section 5.3), after which the Work Program Secretary (WPS) generates reports and posts these on the portal. Previous reports are archived. The portal establishes links between Permanent Documents and the Releases to which they belong and between Releases and the Work Items which describe the scope of the work. On the portal, under the WP tab, each working group will find a list of the assigned Work Items.

### Version 1.1

Updated in relation to Proactive Work Programme Management:

OMA-REL-2008-0128R04-CR_WISPRProc_PRM_Package

OMA-REL-2008-0150-CR_WISPRProc_V1_1_Editorials

OMA-REL-2008-0156-CR_WISPRProc_IntroduceADApproval

OMA-REL-2008-0161-CR_WISPRProc_ClarifyingWISPRHandling

## Version 1.2

Textual changes (simplifications, consistency) The following is a summary of the changes:

No need for a definition of “Technical Plenary”

Removed unused abbreviations

Simplified introduction

Introduce abbreviations at their first occurrence in the text, and subsequently only use the abbreviation and not the expanded term

Aligned the sections on WI champion and IOP champion and elevated text that was applicable to both to the parent section

There was duplication on who applies WISPR changes, and when

Section on delegation was simplified

Align procedures with current practices (e.g. remove references to WISPR-Updates list).

Add an additional RD milestone for “End of new requirements”.

Remove end or RD review and end of AD review milestones

# Elements of the WISPR

## WISPR Components

The Work Item Status and Planning Report (WISPR) information consists of the following components:

- an index page of all releases,

- the RELEASE status description and schedule information up to final approval of the Release,

- interdependencies between OMA Releases,

- the list of unpublished external deliverables normatively referenced by this Release (if applicable),

- the WI Champion and IOP Champion

- other relevant information.

## Responsibilities of the WI and IOP Champions

The Group owning the Work Item (WI) is responsible for the work and the overall planning of the work. To assist with WI status reporting, each WI SHALL name a WI Champion and an IOP Champion. When a WI is transferred to another group, the WG SHALL inform the WPS and indicate if the WI or IOP champion has changed.

### WI Champion

The Group owning the WI  SHALL appoint a WI champion for each version of a Release.. If the Group cannot appoint a WI Champion then the chair will serve as WI Champion.

The WI Champion SHOULD update the target dates, descriptions and linked enablers for the WI.

In case of delegated work (section 6.2.1) the WI Champion is the prime person for tracking and reconciling activities between the affected groups.

### IOP Champion

The IOP Champion is responsible for WISPR tracking and is the primary contact for exchange of IOP information (e.g. progress on IOP documents). An IOP Champion SHALL be appointed for each version of an Enabler Release prior to RD Candidate approval. In case no IOP Champion can be identified prior to RD Candidate Approval, the WI Champion SHALL combine both roles. As the work progresses through the enabler development cycle, the WI champion in agreement with the IOP-WG MAY then subsequently identify another IOP champion, as appropriate and as desired. IOP WG agreement is required to update IOP-related WISPR dates.

## Milestones in the WISPR

WISPR milestones reflect the nominal process steps normally performed during the life-cycle of the work, and are used for progress tracking.

| Milestone | Trigger Event(s) |
| --- | --- |
| RD work Start | First draft RD uploaded as a Permanent Document First input contribution to the RD First time RD is on the meeting agenda |
| New requirements deadline | Announced on RD-DEV and ARC-DEV mailing list |
| Informal RD review | When the input contribution requesting the informal review is “noted” or “agreed” |
| Start of formal RD review | Start of review announced on RD-DEV mailing list |
| RD approved as Candidate | TP approval of the RD either by TP R&A or during a TP face to face meeting |
| Start of AD development | First draft AD uploaded as a Permanent Document First input contribution to the AD First time AD is on the meeting agenda |
| Informal AD review | When the input contribution requesting the informal review is “noted” or “agreed” |
| Start of formal AD review | Start of review announced on AD mailing list |
| AD approved as Candidate | TP approval of the AD either by TP R&A or during a TP face to face meeting |
| Start of Spec/WP development | First draft TS/SUP/WP uploaded as a PD First input contribution to the TS/SUP file/White Paper etc First time TS/SUP file /White Paper is on the meeting agenda |
| Start of Consistency Review | Start of review announced on CONR mailing list |
| ERP/RRP approved as Candidate | TP approval as Candidate during a face to face meeting or TP R&A |
| Start of IOP Activities | ETRRR first uploaded to the portal |
| Test Specifications Complete | Will be replaced by “EVP approved as Candidate” for all active Enablers which do not have an achieved date for “test specifications Complete” . |
| EVP Approved as candidate | EVP approved as Candidate by TP. |
| Test Activities complete | IOP Report sent to REL |
| ERP/RRP final Approval | TP approval as Approved during a face to face meeting or TP R&A |

Table 1: Milestone Determination Events

DSO will monitor the work in the groups they support and SHALL update the Achieved dates in the WP as the triggering event occurs.

# WISPR Procedures

## WISPR information following approval of new WIDs

WIs approved by TP have a schedule for completion of the Candidate release. Following WI approval, WPS SHALL transfer the target dates to the WISPR tool. This is a key factor to ensure that the work appears correctly in all WP reports.

## Required Updates to the WISPR

The WISPR information SHALL be updated by the end of every major Working Group meeting (the five meetings organized on a yearly basis). Some WISPR updates require TP approval (see section 6.2.2)

The WPS will inform the OMA-chairs exploder list of the WISPR update deadlines.

The WI Champion MUST review the dates and press the “Submit” when changes have been made, or the “Reviewed and accepted without change” button  when no changes are needed. WISPR updates MAY be also provided when there are changes between OMA organized Group meetings (for example after an interim Group meeting).

If two WISPR reporting cycles are missed then REL SHOULD check first with the Group and MAY then recommend to TP that the WI should be closed.

### Delegated Work for a Work Item

A WG may delegate part of the work to another group. The delegated group is responsible for carrying out the work within the schedule. Changes to the schedule MUST be agreed with the group which owns the WI. In case of issues, consensus SHALL be sought for a joint work plan. The owning WG SHALL have the final say on the WI schedule.

### Changes to the WISPR Schedule

Changing the following target dates SHALL require TP approval:

Candidate Approval of the Requirements Document

Candidate Approval of the Architecture Document

Candidate Approval of the Release

If TP does not approve the request to change the above target dates, then the existing schedule will continue to apply and TP SHALL provide guidance to the WG on how to proceed. The WG needs to address what to do next in a timely manner, e.g.

Remove functionality

Defer functionality to a subsequent version of a release

Suggest that the WI is closed.

Submit a revised proposal to the TP (i.e combination of a date change request and functionality reduction)

Achieved dates SHALL only be updated by DSO.

## REL Analysis of the Work Program

- Following each WISPR cycle, REL SHALL analyse the WP data and report any issues to WGs for resolution or clarification.

- Interaction between REL and the WGs MAY follow until the issue is resolved

## Process steps and responsibilities for Work programme updates

| Step | Description | Action by Group/WI/WISPR Champion | Action by REL | Action by WPS |
| --- | --- | --- | --- | --- |
| 1. | Initiate update of WISPRs Event trigger: upcoming TP & OMA organised Group meeting. |  |  | Email reminder to Group chairs and WI Champions |
| 2. | Update WISPR information on the portal. | Update the WISPR components (section 5.1). For Releases, work with IOP to update the schedule information for testing milestones. |  |  |
| 3. | Follow up WISPR missing/inconsistent data - Deadline: 7 days after each major OMA WG meeting | Make corrections as highlighted by WPS |  | Highlight errors/omissions to WISPR Champion. |
| 4. | Run WP report - deadline; 21 days after 1. |  |  | Generate reports into pending folder on REL |
| 5. | Review WP reports for publication |  | REL officers review WP reports |  |
| 6. | Produce WP analysis |  | Review in REL Circulate to WGs. Work with WGs to resolve any issues | Produce WP Analysis Work with WGs to resolve any issues |
| 7. | Report unresolved issues to TP |  | Report unresolved issues to TP |  |

Table 2: Process steps

Change History	(Informative)

Approved Version History

| Reference | Date | Description |
| --- | --- | --- |
| OMA-ORG-WISPR_ProceduresV1_0 | 16 Apr 2008 | Approved by TP as OMA-TP-2008-0167-INP_WISPR_Procedures_V_1_0_for_Approval |
| OMA-ORG-WISPR_ProceduresV1_1 | 17 Oct 2008 | Approved by TP as OMA-TP-2008-0410-INP_ORG_WISPR_Proc_V1_1_for_approval |
| OMA-ORG-WISPR_ProceduresV1_2 | 23 Sep 2009 | Approved by TP as OMA-TP-2009-0430-INP_WISPR_procedures_v1_2_for_approval |